## Lab Tool Checklist
Lab and Tool Setup Checklist
Project: Cyber Security Placement — Adversary Test Automation
Area | Task | Priority | Status | Date Completed | Notes
Host | Windows cloud VM setup (confirm access and resources) | High | Completed | 2026-10-09 | 12/10/2026 - New VM requested and provided (with nested virtualisation feature), but unable to connect (still wait for IT team response)
Lab as Code | Set up Vagrant | High | Blocked |  | 09/10/2026 - Nested Virtualisation still need to be confirmed (have asked IT team)
Targets | Windows, Ubuntu (if available) | High | Not Started
| OWASP Juice Shop, C/C++ target | Optional | Not Started
Network | Confirm isolated network, IT approval | High | Not Started |  | 09/10/2026 - Waiting for approval
Telemetry | Sysmon, auditd (if using Ubuntu), Wazuh; confirm telemetry works | High | Not Started |  | 12/10/2026 - Wazuh selected as the proposed central monitoring platform.
Adversary Emulation | Set up and run selected Atomic Red Team tests | High | Not Started
| Explore CALDERA and Stratus Red Team | Optional | Not Started
Network Testing | Set up and run relevant Nuclei tests | High | Not Started
| Explore Scapy, boofuzz, Nmap NSE or tcpreplay | Optional | Not Started
Software Testing | Semgrep and OWASP ZAP Automation Framework | High | Not Started
| Explore AFL++ / libFuzzer / Trivy | Optional | Not Started
Orchestration | Python, pytest; create automated test execution | High | In Progress |  | 09/10/2026 - Python and pytest are installed
| Set up GitHub Actions/self-hosted runner | Optional | Not Started
Reporting | Prepare ATT&CK Navigator; record and store results as JSON | High | Not Started
| Create Sigma rules where required | Optional | Not Started
AI Tooling | Confirm LLM API access and spending limit | High | Not Started
| Create manual test cases | High | Not Started
| Generate LLM test cases | High | Not Started
| Compare LLM-generated and manual tests | High | Not Started
| Explore promptfoo | Optional | Not Started

## Tool Resources
Tool Resources
Area | Tool | Purpose | Resource | Priority
Lab as Code | Vagrant | Lab environment setup | https://developer.hashicorp.com/vagrant | High
| Terraform | Infrastructure as code | https://developer.hashicorp.com/terraform/docs | Optional
| Ludus | Prebuilt cyber range/lab setup | https://ludus.cloud/ | Optional
| Docker Compose | Software target setup | https://docs.docker.com/compose/ | Optional
Telemetry | Sysmon | Windows telemetry | https://learn.microsoft.com/en-us/sysinternals/downloads/sysmon | High
| Winlogbeat | Windows event log collection | https://www.elastic.co/docs/reference/beats/winlogbeat | Optional
| auditd | Linux system auditing | https://manpages.ubuntu.com/manpages/noble/man8/auditd.8.html | High
| Elastic Stack | Telemetry storage, search and analysis | https://www.elastic.co/docs/get-started/the-stack | Optional
| Wazuh | Security monitoring and telemetry | https://documentation.wazuh.com/current/index.html | High
Adversary Emulation | Atomic Red Team | Adversary technique testing | https://github.com/redcanaryco/atomic-red-team | High
| MITRE CALDERA | Adversary emulation | https://github.com/mitre/caldera | Optional
| Stratus Red Team | Cloud adversary emulation | https://github.com/DataDog/stratus-red-team | Optional
Network Testing | Scapy | Network packet testing | https://scapy.readthedocs.io/en/stable/ | Optional
| boofuzz | Network protocol fuzzing | https://github.com/jtpereyda/boofuzz | Optional
| Nmap NSE | Network testing and scripting | https://nmap.org/book/nse.html | Optional
| Nuclei | Automated security testing | https://github.com/projectdiscovery/nuclei | High
| tcpreplay | Network traffic replay | https://tcpreplay.appneta.com/ | Optional
Software Testing | AFL++ | Software fuzzing | https://github.com/AFLplusplus/AFLplusplus | Optional
| libFuzzer | Coverage-guided fuzz testing | https://llvm.org/docs/LibFuzzer.html | Optional
| Semgrep | Automated code security analysis | https://semgrep.dev/ | High
| OWASP ZAP Automation Framework | Web application security testing and automation | https://www.zaproxy.org/docs/automate/automation-framework/ | High
| Trivy | Security scanning | https://trivy.dev/ | Optional
Orchestration | Python | Automation and scripting | https://www.python.org/ | High
| pytest | Automated test execution | https://docs.pytest.org/en/stable/ | High
| GitHub Actions Self-hosted Runner | CI and automated test execution | https://docs.github.com/en/actions/hosting-your-own-runners | Optional
Reporting | MITRE ATT&CK Navigator | ATT&CK mapping and reporting | https://github.com/mitre-attack/attack-navigator | High
| Sigma | Security detection rules | https://github.com/SigmaHQ/sigma | Optional
AI Tooling | LLM API | Generate cybersecurity test cases | TBC | High
| promptfoo | Evaluate LLM outputs | https://github.com/promptfoo/promptfoo | Optional

## Access Approvals
Required Access / Approvals
Requirement | Status | Notes
IT approval for isolated network (in writing) | In Progress | Requested: 09/10/2026
Windows cloud VM | Completed | Requested: 6/10/2026 Expected: 9/10/2026
GitHub organisation/private repository | In Progress | Requested: 09/10/2026
Rules of engagement | In Progress | Requested: 09/10/2026
Student acceptable-use declaration | In Progress | Requested: 09/10/2027
Self-hosted runner access (if required) | Not Started
LLM API access/spending limit | Not Started

## Notes
Additional Note
1. Use Lab Tool Checklist as the main progress tracker.
2. Use Tool Resources to open official installation/documentation pages.
3. Complete Priority tasks before Optional tasks where practical.
4. Update Status, Date Completed and Notes as work progresses.
5. Do not store installer files, credentials, API keys, raw telemetry or other sensitive material in GitHub.
6. Install and run security tools only within the authorised project environment and according to the agreed rules of engagement.
7. Tool selection may change based on available infrastructure, supervisor feedback, technical feasibility, time and project requirements.